## Program Planner
|  | Topic | Initiative | Actions | Start Date | End Date | Status | Accountable | Notes
ESTABLISH PHASE
👤 PEOPLE
Establish | Process | ▸ Stable, Credible Leadership Pipeline | ◈ Board, LC, LD | Define Org structure and roles |  |  | Completed |  |  | Not Started
|  |  |  | Categorise talent using A1–C2 framework (Performance × Potential × Values overlay) to identify retention priorities |  | 2026-05-18 | Not Started |  |  | Completed
|  |  |  | Hiring for new roles and replacement |  | 2026-06-12 | In-Progress |  |  | Blocked
|  |  | ◈ Special Roles | Define Org structure and roles |  |  | Completed
|  |  |  | Hire for special new roles |  | 2026-06-12 | In-Progress
|  |  | ◈ High Potentials | Conduct Talent categorization on A1–C2 grid (Values integrated alongside Performance & Potential) |  | 2026-05-20 | Not Started
|  |  |  | Redesign recognition mechanisms for A1/A2/B1 talent (differentiated rewards, sponsor programs, stretch assignments) |  | 2026-05-27 | Not Started
|  |  |  | Design L&D Programs for accelerated leadership (Hi-Po cohorts, leadership accelerators, succession-linked pathways) |  | 2026-05-27 | Not Started
|  |  | ◈ Talent and Retention Structures | Assess current attrition rate, regrettable-loss patterns, and retention gaps by talent tier (A/B/C grid) |  | 2026-05-27 | Not Started
|  |  |  | Design retention framework: comp interventions, career interventions, sponsor interventions per talent tier |  | 2026-06-04 | Not Started
|  |  | ◈ Hire Young Leaders | Design campus engagement programs |  | 2026-05-22 | Not Started
|  |  |  | Create young leader development framework |  | 2026-05-27 | Not Started
|  |  |  | Build long-term leadership pipeline metrics |  | 2026-06-12 | Not Started
|  | ▸ Performance Management | ◈ OKRs / KPIs / Goals Set | Define SSC-wide transformation objectives |  | 2026-06-05 | Not Started
|  |  |  | Create function-wise KPIs aligned to GCC goals |  | 2026-06-12 | Not Started
|  |  |  | Policy deployment via X-matrix: cascade goals via catch-ball; ensure vertical alignment + horizontal connectivity |  | 2026-06-01 | Not Started
|  |  | ◈ Performance Based Incentives Introduced | Create performance-linked reward framework |  | 2026-06-01 | Not Started
|  |  |  | Align incentives to productivity and goals |  | 2026-06-12 | Not Started
|  |  |  | Obtain leadership and HR approvals |  | 2026-06-26 | Not Started
|  |  |  | Communicate incentive model transparently |  | 2026-05-31 | Not Started
|  | ▸ Self-sustaining Talent Ecosystem | ◈ Higher Standard Recruitment Process | Review current hiring effectiveness and gaps |  |  | Not Started
|  |  |  | Redesign recruitment process for GCC readiness |  |  | Not Started
|  |  |  | Create competency based standardized assessment models |  |  | Not Started
|  |  |  | Establish recruitment SLAs and dashboards |  |  | Not Started
|  |  |  | Create quality-of-hire tracking mechanism |  |  | Not Started
|  |  | ◈ Continuous Upgrading of Roles | Assess current role structures and capability maturity |  |  | Not Started
|  |  |  | Identify evolving business, digital, and operational skill requirements |  |  | Not Started
|  |  |  | Map future-ready competencies across functions and roles |  |  | Not Started
|  |  |  | Redesign roles to align with emerging technologies and business needs |  |  | Not Started
|  | ▸ Design and Execute an Attractive EVP | ◈ Build a Brand Story on Select Media |  |  |  | In-Progress
|  |  |  | Create branding themes aligned with company vision |  |  | In-Progress
|  |  |  | Create branding campaigns for LinkedIn and other media platforms |  |  | Not Started
|  |  |  | Track engagement and employer brand metrics |  |  | Not Started
|  |  | ◈ Represent GMR GCC in Key Events | Identify industry conferences and GCC forums |  |  | Not Started
|  |  |  | GCC newsboard with curated GCC related news |  |  | Not Started
|  |  |  | Execution & Implementation |  |  | Not Started
⚙️ PROCESS
Establish | Process | ▸ Move from Projects to Continuous Improvement Culture | ◈ Enable through Modern Six Sigma | AS-IS diagnostic of current Business Excellence practice |  |  | Not Started
|  |  |  | Deploy agnostic Problem Solving toolkit (Lean, Six Sigma, design thinking, RCA, AI-assisted) |  |  | Not Started
|  |  |  | MAGIC waves kick off; first 3 PS projects chartered |  |  | Not Started
|  |  |  | Launch MAGIC platform (Make All Great Ideas Count) — pilot wave |  |  | Not Started
|  |  |  | CI Champions network seeded across HR, Procurement, Finance |  |  | Not Started
|  |  | ◈ Enable through Agile / SAFe Implementation | Agile Scrum Master onboarded​ |  |  | Not Started
|  |  |  | Agile primer for CI CoE + PMO​ |  |  | Not Started
|  |  |  | First 2 squads stood up (S/4 + automation)​ |  |  | Not Started
|  |  |  | Sprint cadence & ceremonies established |  |  | Not Started
|  |  | ◈ Enable through Mining, RPA, AI, Data Analytics | Process Mining POC on 1–2 priority processes​ |  |  | Not Started
|  |  |  | RPA opportunity scan & bot pipeline​ |  |  | Not Started
|  |  |  | Data & analytics foundation (KPI dashboards)​ |  |  | Not Started
|  |  |  | AI / GenAI use-case shortlist |  |  | Not Started
|  |  | ◈ Ensure On Time and In Full S/4 Deliverables | CI war-room joins S/4 program governance​ |  |  | Not Started
|  |  |  | OTIF risk register & weekly heatmap​ |  |  | Not Started
|  |  |  | Value Capture Office for S/4 benefits​ |  |  | Not Started
|  |  |  | Cutover readiness checks​ |  |  | Not Started
|  | ▸ Portfolio Expansion – In-house Consulting | ◈ Problem Solving | AS-IS diagnostic of Business Excellence​ |  |  | Not Started
|  |  |  | Deploy agnostic Problem-Solving toolkit​ |  |  | Not Started
|  |  |  | First 3 problem solving initiatives chartered​ |  |  | Not Started
|  |  | ◈ Project Management | Identify project management capabilities required across functions |  |  | Not Started
|  |  |  | Create PMO organization structure and governance model |  |  | Not Started
|  |  |  | Train teams on Agile, Waterfall, and hybrid delivery approaches |  |  | Not Started
|  |  |  | Establish project management capability-building programs |  |  | Not Started
|  |  |  | Create reusable toolkits, dashboards, and governance assets |  |  | Not Started
|  |  |  | Launch pilot PMO engagements for internal business units |  |  | Not Started
|  |  |  | Define PMO KPIs and service performance metrics |  |  | Not Started
|  |  | ◈ Change Management Automation | Identify change management service areas for business functions |  |  | Not Started
|  |  |  | Build training and adoption management capabilities |  |  | Not Started
|  |  |  | Create change readiness and impact assessment templates |  |  | Not Started
Not Started
|  |  |  | Launch pilot change management engagements for transformation initiatives |  |  | Not Started
|  |  |  | Define KPIs for adoption, engagement, and transformation success |  |  | Not Started
|  |  | ◈ Analytics | Assess current reporting and analytics maturity |  |  | Not Started
|  |  |  | Build analytics capability within teams |  |  | Not Started
|  |  |  | Identify business-critical analytics use cases |  |  | Not Started
|  |  |  | Define analytics operating model |  |  | Not Started
|  |  |  | Build centralized reporting standards |  |  | Not Started
|  |  |  | Create KPI dashboards and management reporting |  |  | Not Started
💻 TECHNOLOGY
Establish | Technology | ▸ S/4 HANA | ◈ 100% S4 Adoption | Assess current ERP usage and adoption gaps |  |  | Completed
|  |  |  | Setup regular cadences with EY |  |  | Not Started
|  |  |  | Monitor adoption and system usage metrics |  |  | Not Started
|  |  | ◈ Tech Integrated Problem Solving and Solutioning | Identify operational challenges suitable for digital solution |  |  | Not Started
|  |  |  | Track technology-driven efficiency improvements |  |  | Not Started
|  |  |  | Monitor adoption and system usage metrics |  |  | Not Started
ENHANCE PHASE
👤 PEOPLE
Enhance | People | ▸ Brand Campaign | ◈ Launch Internal Brand Campaign that Showcases Momentum | Define campaign Startegy, objectives and messaging |  |  | Not Started
|  |  |  | Identify value themes and success stories |  |  | Not Started
|  |  |  | Develop communication calendar |  |  | Not Started
|  |  |  | Create campaign assets and templates |  |  | Not Started
|  |  |  | Launch internal engagement activities |  |  | Not Started
|  |  |  | Measure campaign reach and participation |  |  | Not Started
|  |  |  | Collect feedback and refine messaging |  |  | Not Started
|  | ▸ New Ways of Working | ◈ Impact Rituals Designed and Implemented | Assess current collaboration practices |  |  | In-Progress
|  |  |  | Identify high-impact rituals and ceremonies |  |  | Not Started
|  |  |  | Define governance and participation structure |  |  | Not Started
|  |  |  | Pilot rituals across selected teams |  |  | Not Started
|  |  |  | Roll out organization-wide adoption plan |  |  | Not Started
|  |  |  | Monitor participation and effectiveness |  |  | Not Started
|  |  |  | Standardize successful practices |  |  | Not Started
|  |  | ◈ Capability-building Programs | Conduct capability gap assessment |  |  | Not Started
|  |  |  | Identify priority skill areas |  |  | Not Started
|  |  |  | Design learning curriculum and pathways |  |  | Not Started
|  |  |  | Finalize learning partners/platforms |  |  | Not Started
|  |  |  | Launch training and workshops |  |  | Not Started
|  |  |  | Track learning completion and effectiveness |  |  | Not Started
|  |  |  | Establish continuous learning cadence |  |  | Not Started
|  | ▸ People Development | ◈ Job Architectures & Career Paths Set Up | Phase I — Discovery & framework design: scope, sponsors, CORE group (regional HRBPs); approved by Steering |  |  | Not Started
|  |  |  | Phase II — Build Global Job Families & Sub-Families: regional inputs → consolidation → CORE workshop → v1.0 sign-off |  |  | Not Started
|  |  |  | Phase III — Define 7-Level Career Architecture with 4 tracks (Professional / Management / Leadership / Specialist-IC); manages-managers split for Mgmt→Leadership |  |  | Not Started
|  |  |  | Phase IV — Role mapping: every active employee → JF/SJF/Level/Track/Grade via Mapping Toolkit; manager + HRBP calibration |  |  | Not Started
|  |  |  | Phase V — 15-Grade Pay Structure benchmarked (Salary.com); equity check; remediation plan; Board approval |  |  | Not Started
|  |  |  | Phase VI — Go-live: HRIS configuration, manager enablement, employee comms, appeals window, embed in promo/hiring cycles |  |  | Not Started
|  |  |  | Sustain (Gen 2) — Annual refresh, skills overlay, integration with talent reviews, internal mobility, and L&D pathways |  |  | Not Started
|  |  | ◈ Create Holistic Growth Plan for All Employees | Define HGP framework and templates |  |  | Not Started
|  |  |  | Align personal and organizational goals |  |  | Not Started
|  |  |  | Conduct manager enablement sessions |  |  | Not Started
|  |  |  | Launch employee onboarding sessions |  |  | Not Started
|  |  |  | Track goal-setting completion |  |  | Not Started
|  |  |  | Conduct periodic progress reviews |  |  | Not Started
|  |  |  | Refine framework based on feedback |  |  | Not Started
|  |  | ◈ Learning & Development Plan | Assess current learning maturity |  |  | Not Started
|  |  |  | Identify business-critical skill requirements |  |  | Not Started
|  |  |  | Define annual learning roadmap |  |  | Not Started
|  |  |  | Create functional and behavioral learning tracks |  |  | Not Started
|  |  |  | Launch development interventions |  |  | Not Started
|  |  |  | Measure learning effectiveness and adoption |  |  | Not Started
|  |  |  | Continuously refresh learning programs |  |  | Not Started
⚙️ PROCESS
Enhance | Process | ▸ Continuous Improvement Becomes a Way of Life | ◈ Set Up a Well-functioning CI Engine | Define CI governance structure and operating model (MAGIC: Capture-Evaluate-Execute-Measure-Accolade) |  | 2026-06-06 | In-Progress
|  |  |  | MAGIC platform wave-2 scale-out across all functions |  | 2026-06-20 | Not Started
|  |  |  | PS at scale; first Green Belt cohort chartered |  | 2026-07-13 | Not Started
|  |  |  | Recognition program live (badges, scorecards, belt cert progression) |  | 2026-08-31 | Not Started
|  |  |  | Establish CI KPI dashboards (ideas submitted, projects active, savings, participation) |  |  | Not Started
|  |  |  | Review CI impact and sustainability; tune the engine |  |  | Not Started
|  |  | ◈ Set Up an Innovation Hub | Define Innovation Hub charter, governance, and intake mechanism |  |  | Not Started
|  |  |  | Identify innovation focus areas (digital, AI/GenAI, process re-imagination) |  |  | Not Started
|  |  |  | Establish Idea-to-Impact pipeline (intake → triage → POC → scale) |  |  | Not Started
|  |  |  | Launch 2-3 pilot innovation initiatives with measurable outcomes |  |  | Not Started
|  |  |  | Set up Innovation KPI tracking (idea volume, POC velocity, scale rate, value) |  |  | Not Started
|  |  |  | Drive innovation culture through hackathons, GenAI sandboxes, cross-functional sprints |  |  | Not Started
|  | ▸ Core Business Function Pilot | ◈ Identify & Pilot Core Business Functions | Identify functions for pilot transition |  |  | Not Started
|  |  |  | Assess process readiness and dependencies |  |  | Not Started
|  |  |  | Define pilot scope and success criteria |  |  | Not Started
|  |  |  | Establish transition governance structure |  |  | Not Started
|  |  |  | Execute pilot operations |  |  | Not Started
|  |  |  | Capture learnings and optimize model |  |  | Not Started
|  | ▸ CoE Transition | ◈ HR CoE | Identify HR services for SSC transition |  |  | Not Started
|  |  |  | Assess process standardization readiness |  |  | Not Started
|  |  |  | Define centralized HR operating model |  |  | Not Started
|  |  |  | Establish service ownership and governance |  |  | Not Started
|  |  |  | Design SLA and service delivery framework |  |  | Not Started
|  |  |  | Transition prioritized HR processes |  |  | Not Started
|  |  |  | Enable reporting and performance tracking |  |  | Not Started
|  |  |  | Stabilize operations and optimize delivery |  |  | Not Started
|  |  | ◈ Procurement CoE | Identify procurement activities for transition |  |  | Not Started
|  |  |  | Assess procurement process maturity and scalability |  |  | Not Started
|  |  |  | Define centralized procurement operating structure |  |  | Not Started
|  |  |  | Standardize sourcing and procurement workflows |  |  | Not Started
|  |  |  | Establish governance and escalation mechanisms |  |  | Not Started
|  |  |  | Transition pilot procurement operations |  |  | Not Started
|  |  |  | Enable compliance and reporting controls |  |  | Not Started
|  |  |  | Monitor efficiency and value realization |  |  | Not Started
|  |  | ◈ MDM CoE | Identify master data activities for transition |  |  | Not Started
|  |  |  | Define enterprise data ownership structure |  |  | Not Started
|  |  |  | Standardize master data governance processes |  |  | Not Started
|  |  |  | Establish data quality and control mechanisms |  |  | Not Started
|  |  |  | Transition prioritized data management activities |  |  | Not Started
|  |  |  | Enable centralized reporting and monitoring |  |  | Not Started
|  |  |  | Conduct business adoption and governance reviews |  |  | Not Started
|  |  |  | Optimize data management effectiveness |  |  | Not Started
💻 TECHNOLOGY
Enhance | Technology | ▸ Automation Strategy | ◈ Harmonize Mining, RPA, AI, Data Analytics | Assess current automation initiatives |  |  | Not Started
|  |  |  | Identify overlapping and scalable opportunities |  |  | Not Started
|  |  |  | Define enterprise automation framework |  |  | Not Started
|  |  |  | Prioritize use cases by business impact |  |  | Not Started
|  |  |  | Establish implementation roadmap |  |  | Not Started
|  |  |  | Enable centralized monitoring and governance |  |  | Not Started
|  |  |  | Measure automation adoption and value realization |  |  | Not Started
OPTIMIZE PHASE
👤 PEOPLE
Optimize | People | ▸ Performance Culture | ◈ Measures Designed to Shift & Sustain High Performance and Ownership Culture | Define enterprise performance culture principles & Integrate GMR Values within it |  |  | Not Started
|  |  |  | Align KPIs with business and transformation goals |  |  | Not Started
|  |  |  | Establish ownership-driven performance mechanisms |  |  | Not Started
|  |  |  | Embed performance review and feedback cadence |  |  | Not Started
|  |  |  | Introduce recognition and reward frameworks |  |  | Not Started
|  |  |  | Track culture and performance maturity indicators |  |  | Not Started
|  |  |  | Continuously refine performance interventions |  |  | Not Started
|  | ▸ Learning Organization | ◈ New Ways of Working Sustained | Assess adoption maturity of new ways of working |  |  | Not Started
|  |  |  | Institutionalize agile and collaborative practices |  |  | Not Started
|  |  |  | Embed continuous learning into workflows |  |  | Not Started
|  |  |  | Establish cross-functional knowledge-sharing forums |  |  | Not Started
|  |  |  | Promote experimentation and innovation culture |  |  | Not Started
|  |  |  | Measure adoption and effectiveness metrics |  |  | Not Started
|  |  |  | Optimize learning and collaboration mechanisms |  |  | Not Started
|  | ▸ Employee Experience | ◈ Redesign Employee Life Cycle | Assess employee lifecycle experience gaps |  |  | Not Started
|  |  |  | Redesign key employee journey touchpoints |  |  | Not Started
|  |  |  | Standardize experience across functions |  |  | Not Started
|  |  |  | Enable digital employee experience solutions |  |  | Not Started
|  |  |  | Embed feedback and listening mechanisms |  |  | Not Started
|  |  |  | Track employee engagement and satisfaction metrics |  |  | Not Started
|  |  |  | Continuous improvement employee experience framework Mechanism set |  |  | Not Started
⚙️ PROCESS
Optimize | Process | ▸ Core Business Transitions | ◈ Identification of Core Business Support to be Transitioned | Identify strategic business capabilities for transition |  |  | Not Started
|  |  |  | Assess transition feasibility and business impact |  |  | Not Started
|  |  |  | Prioritize functions based on value and readiness |  |  | Not Started
|  |  |  | Define transition governance and ownership |  |  | Not Started
|  |  |  | Execute phased transition roadmap |  |  | Not Started
|  |  |  | Monitor transition effectiveness and business continuity |  |  | Not Started
|  |  |  | Optimize integrated service delivery model |  |  | Not Started
|  | ▸ Process Excellence | ◈ Processes Documented and Measured Constantly | Standardize enterprise process documentation and knowledge repositories |  |  | Not Started
|  |  |  | Define critical process KPIs and operational dashboards |  |  | Not Started
|  |  |  | Establish process governance and review mechanisms |  |  | Not Started
|  |  |  | Enable real-time process visibility and tracking |  |  | Not Started
|  |  |  | Embed continuous improvement into operational workflows |  |  | Not Started
|  |  |  | Identify process optimization and digitalization opportunities |  |  | Not Started
|  |  |  | Drive data-driven operational decision-making |  |  | Not Started
|  |  |  | Continuously enhance efficiency, quality, and service delivery |  |  | Not Started
|  |  | ◈ Global Standards Maintained | Benchmark capabilities against global GCC and industry practices |  |  | Not Started
|  |  |  | Assess gaps in current operational and service standards |  |  | Not Started
|  |  |  | Establish enterprise-wide operational and service standards |  |  | Not Started
|  |  |  | Align GCC processes with global business and compliance expectations |  |  | Not Started
|  |  |  | Standardize governance, controls, and quality frameworks |  |  | Not Started
|  |  |  | Enable centralized monitoring of process adherence and risks |  |  | Not Started
|  |  |  | Conduct periodic operational maturity and standards reviews |  |  | Not Started
|  |  |  | Continuously enhance quality, consistency, and operational reliability |  |  | Not Started
|  |  | ◈ Push for Max Digital | Identify digital transformation opportunities |  |  | Not Started
|  |  |  | Assess and prioritize digital initiatives based on business impact and feasibility |  |  | Not Started
|  |  |  | Establish digital governance and transformation management frameworks |  |  | Not Started
|  |  |  | Accelerate adoption of automation, AI, and intelligent workflows |  |  | Not Started
|  |  |  | Improve adoption of digital platforms and capabilities across functions |  |  | Not Started
|  |  |  | Enable data-driven and insight-led decision-making practices |  |  | Not Started
|  |  |  | Continuously enhance digital maturity and operational agility |  |  | Not Started
💻 TECHNOLOGY
Optimize | Technology | ▸ Reposition Tech as Enabler and Align | ◈ Tech ← Process ← People | Assess gaps between business processes, people capabilities, and technology enablement |  |  | Not Started
|  |  |  | Identify high-impact opportunities where technology can improve operational effectiveness |  |  | Not Started
|  |  |  | Define integrated business-process-technology transformation priorities |  |  | Not Started
|  |  |  | Establish cross-functional governance between business, operations, and technology teams |  |  | Not Started
|  |  |  | Align technology solutions with process and employee experience needs |  |  | Not Started
|  |  |  | Enable adoption of integrated digital workflows across functions |  |  | Not Started
|  |  |  | Monitor business impact, operational efficiency, and user adoption |  |  | Not Started
|  |  |  | Continuously optimize technology enablement across GCC operations |  |  | Not Started
|  | ▸ Tech Embedded Capability Building | ◈ Develop Techno-Functional Expertise | Assess future-ready techno-functional capability requirements across functions |  |  | Not Started
|  |  |  | Identify critical digital, operational, and domain skill gaps |  |  | Not Started
|  |  |  | Define integrated techno-functional learning pathways |  |  | Not Started
|  |  |  | Enable hands-on learning through business-driven use cases and projects |  |  | Not Started
|  |  |  | Build specialized expertise in digital, automation, analytics, and AI capabilities |  |  | Not Started
|  |  |  | Encourage cross-functional collaboration and knowledge-sharing practices |  |  | Not Started
|  |  |  | Measure capability maturity and business applicability |  |  | Not Started
|  |  |  | Continuously strengthen future-ready workforce capabilities |  |  | Not Started
|  |  | ◈ Encourage Rapid Prototyping and Innovation | Identify business challenges suitable for rapid experimentation and innovation |  |  | Not Started
|  |  |  | Establish innovation governance and prioritization mechanisms |  |  | Not Started
|  |  |  | Enable sandbox environments and pilot frameworks for experimentation |  |  | Not Started
|  |  |  | Conduct innovation sprints and rapid prototyping initiatives |  |  | Not Started
|  |  |  | Evaluate feasibility, scalability, and business impact of proposed solutions |  |  | Not Started
|  |  |  | Transition successful prototypes into operational implementation |  |  | Not Started
|  |  |  | Promote a culture of experimentation and continuous innovation |  |  | Not Started
|  |  |  | Track innovation outcomes and enterprise value realization |  |  | Not Started
|  |  | ◈ Problem Solving in the Era of AI | Build AI awareness and capability development programs |  |  | Not Started
|  |  |  | Assess AI readiness across business functions and teams |  |  | Not Started
|  |  |  | Conduct AI opportunity assessment workshops across functions |  |  | Not Started
|  |  |  | Identify high-impact operational and business use cases for AI adoption |  |  | Not Started
|  |  |  | Establish responsible AI governance and usage frameworks |  |  | Not Started
|  |  |  | Enable AI-assisted decision-making and operational workflows |  |  | Not Started
|  |  |  | Promote human-AI collaboration across functions |  |  | Not Started
|  |  |  | Measure AI adoption, effectiveness, and business outcomes |  |  | Not Started
|  |  |  | Continuously evolve AI-enabled ways of working and problem-solving capabilities |  |  | Not Started

## Establish (hidden)
Phase | Category | Topic / Initiative | Initiative | Tasks | Phase | Category | Topic / Initiative | Initiative | Updated Task Statements
Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Assess leadership structure and capability gaps | Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Evaluate leadership structure and organizational readiness
Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Define governance, roles, and accountability framework | Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Architect governance and leadership accountability model
Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Develop succession and leadership retention strategy | Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Build succession and leadership continuity strategy
Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Identify workforce gaps and future leadership roles | Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Map critical leadership and workforce capability needs
Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Drive hiring and recruitment for critical roles | Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Launch strategic hiring for key leadership positions
Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Establish leadership performance and operating cadence | Establish | People | Stable, Credible Leadership Pipeline | Board, LC, LD | Institutionalize leadership review and governance rhythm
Phase | Category | Topic | Initiative | Tasks | Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Analyze specialized role and capability requirements
Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Identify critical and specialised roles | Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Design role structures and responsibility frameworks
Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Define role scope and responsibilities | Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Build competency and skill requirement models
Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Develop competency and skill requirements | Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Create career pathways for specialized roles
Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Create role descriptions and career paths | Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Evaluate talent availability and capability gaps
Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Assess resource availability and gaps | Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Activate hiring for niche and specialized capabilities
Establish | People | Stable, Credible Leadership Pipeline | Special Roles | Initiate hiring for specialised roles | Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Identify high-potential talent across functions
Phase | Category | Topic | Initiative | Tasks | Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Evaluate leadership potential and readiness levels
Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Identify high-potential employees | Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Design succession and growth acceleration framework
Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Conduct talent assessment and evaluation | Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Build mentoring and leadership development pathways
Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Define succession planning framework | Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Launch engagement programs for emerging leaders
Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Create leadership development plans | Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Monitor leadership progression and talent readiness
Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Establish mentoring and coaching programs | Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Analyze workforce retention risks and attrition drivers
Establish | People | Stable, Credible Leadership Pipeline | High Potentials | Track performance and readiness progress | Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Architect talent retention and career growth framework
Phase | Category | Topic | Initiative | Tasks | Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Build performance and reward alignment structures
Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Assess workforce retention risks | Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Launch workforce engagement and retention initiatives
Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Define talent retention strategy | Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Strengthen hiring for business-critical talent gaps
Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Establish career progression framework | Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Sustain retention governance and workforce reviews
Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Design performance and reward structures | Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Analyze future leadership and capability demands
Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Launch employee engagement initiatives | Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Design young leadership acquisition framework
Establish | People | Stable, Credible Leadership Pipeline | Talent and Retention Structures | Monitor retention and attrition metrics | Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Build campus and emerging talent engagement channels
Phase | Category | Topic | Initiative | Tasks | Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Execute recruitment and assessment initiatives
Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Define young leadership hiring strategy | Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Roll out onboarding and leadership readiness programs
Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Identify future leadership skill requirements | Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Track young leadership pipeline effectiveness
Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Build campus and talent acquisition channels | Establish | People | Performance Management | OKRs / KPIs / Goals Set | Review current performance and goal-setting maturity
Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Conduct recruitment and assessment drives | Establish | People | Performance Management | OKRs / KPIs / Goals Set | Design enterprise OKR and KPI governance model
Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Launch onboarding and leadership training | Establish | People | Performance Management | OKRs / KPIs / Goals Set | Build function-wise performance measurement structures
Establish | People | Stable, Credible Leadership Pipeline | Hire Young Leaders | Track leadership pipeline development | Establish | People | Performance Management | OKRs / KPIs / Goals Set | Launch goal alignment and performance workshops
Phase | Category | Topic | Initiative | Tasks | Establish | People | Performance Management | OKRs / KPIs / Goals Set | Embed KPI visibility and reporting mechanisms
Establish | People | Performance Management | OKRs / KPIs / Goals Set | Assess current performance management framework | Establish | People | Performance Management | OKRs / KPIs / Goals Set | Sustain performance review and accountability cadence
Establish | People | Performance Management | OKRs / KPIs / Goals Set | Define OKR, KPI, and goal-setting framework | Establish | People | Performance Management | Performance Based Incentives Introduced | Assess current incentive effectiveness and alignment
Establish | People | Performance Management | OKRs / KPIs / Goals Set | Develop function-wise performance metrics | Establish | People | Performance Management | Performance Based Incentives Introduced | Design performance-linked rewards framework
Establish | People | Performance Management | OKRs / KPIs / Goals Set | Initiate goal-setting and alignment workshops | Establish | People | Performance Management | Performance Based Incentives Introduced | Build incentive eligibility and measurement criteria
Establish | People | Performance Management | OKRs / KPIs / Goals Set | Enable KPI tracking and reporting mechanisms | Establish | People | Performance Management | Performance Based Incentives Introduced | Roll out incentive communication and adoption activities
Establish | People | Performance Management | OKRs / KPIs / Goals Set | Establish performance review cadence | Establish | People | Performance Management | Performance Based Incentives Introduced | Align incentive mechanisms with business outcomes
Phase | Category | Topic | Initiative | Tasks | Establish | People | Performance Management | Performance Based Incentives Introduced | Institutionalize incentive governance and review cadence
Establish | People | Performance Management | Performance Based Incentives Introduced | Assess current rewards and incentive structure | Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Diagnose recruitment gaps and hiring inefficiencies
Establish | People | Performance Management | Performance Based Incentives Introduced | Define performance-linked incentive framework | Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Design GCC-ready recruitment operating framework
Establish | People | Performance Management | Performance Based Incentives Introduced | Develop incentive eligibility and measurement criteria | Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Build competency-based assessment mechanisms
Establish | People | Performance Management | Performance Based Incentives Introduced | Initiate incentive communication and rollout plan | Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Operationalize standardized hiring and evaluation practices
Establish | People | Performance Management | Performance Based Incentives Introduced | Align incentives with KPIs and business goals | Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Embed recruitment performance and SLA tracking
Establish | People | Performance Management | Performance Based Incentives Introduced | Establish incentive review and governance cadence | Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Sustain recruitment governance and review mechanisms
Phase | Category | Topic | Initiative | Tasks | Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Evaluate current role maturity and capability relevance
Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Assess current recruitment process and gaps | Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Design future-ready role and competency architecture
Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Define GCC-ready recruitment framework | Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Build role transition and skill enhancement roadmap
Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Develop competency-based assessment models | Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Launch capability upgrade and role transformation initiatives
Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Initiate standardised hiring and evaluation process | Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Strengthen niche capability acquisition and onboarding
Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Enable recruitment dashboards and SLA tracking | Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Institutionalize role review and modernization cadence
Establish | People | Self-sustaining Talent Ecosystem | Higher Standard Recruitment Process | Establish recruitment governance cadence | Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Assess employer brand visibility and positioning maturity
Phase | Category | Topic | Initiative | Tasks | Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Design EVP communication and branding strategy
Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Assess current role structures and capability maturity | Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Build branding narratives and media engagement assets
Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Define future-ready role and competency framework | Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Roll out employer branding campaigns across channels
Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Develop role redesign and skill upgrade roadmap | Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Monitor employer brand reach and engagement metrics
Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Initiate role transition and capability enhancement programs | Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Sustain branding governance and communication rhythm
Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Hire niche talent for emerging capability areas | Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Evaluate strategic event participation opportunities
Establish | People | Self-sustaining Talent Ecosystem | Continuous Upgrading of Roles | Establish role review and upgrade cadence | Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Define external representation and engagement strategy
Phase | Category | Topic | Initiative | Tasks | Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Develop GCC branding and event communication assets
Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Assess current employer branding presence | Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Activate participation in industry and GCC forums
Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Define EVP branding and communication strategy | Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Measure event visibility and stakeholder engagement
Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Develop branding themes and media content | Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Maintain event participation and review governance
Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Initiate branding campaigns across media platforms
Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Enable employer brand performance tracking
Establish | People | Design and Execute an Attractive EVP | Build a Brand Story on Select Media | Establish branding review and engagement cadence
Phase | Category | Topic | Initiative | Tasks
Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Assess industry event participation opportunities
Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Define event participation and representation strategy
Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Develop GCC event communication and branding assets
Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Initiate participation in industry and GCC forums
Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Enable event impact and engagement tracking
Establish | People | Design and Execute an Attractive EVP | Represent GMR GCC in Key Events | Establish event participation review cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Modern Six Sigma | Assess current process maturity and inefficiencies
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Modern Six Sigma | Define Lean Six Sigma improvement framework
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Modern Six Sigma | Develop process improvement and benefits tracking model
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Modern Six Sigma | Initiate Lean Six Sigma training programs
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Modern Six Sigma | Launch process improvement initiatives
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Modern Six Sigma | Establish improvement review and governance cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Agile / SAFe Implementation | Assess current agile maturity and delivery gaps
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Agile / SAFe Implementation | Define Agile and SAFe operating framework
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Agile / SAFe Implementation | Develop squad structure and delivery governance
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Agile / SAFe Implementation | Initiate Agile coaching and team onboarding
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Agile / SAFe Implementation | Launch Agile ceremonies and sprint execution
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Agile / SAFe Implementation | Establish Agile performance and review cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Mining, RPA, AI, Data Analytics | Assess automation and analytics opportunities
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Mining, RPA, AI, Data Analytics | Define automation and analytics roadmap
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Mining, RPA, AI, Data Analytics | Develop process mining and KPI dashboard framework
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Mining, RPA, AI, Data Analytics | Initiate RPA, AI, and analytics pilot programs
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Mining, RPA, AI, Data Analytics | Hire or onboard digital and analytics capabilities
Establish | Process | Move from Projects to Continuous Improvement Culture | Enable through Mining, RPA, AI, Data Analytics | Establish automation governance and review cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Move from Projects to Continuous Improvement Culture | Ensure On Time and In Full S/4 Deliverables | Assess S/4 delivery risks and dependencies
Establish | Process | Move from Projects to Continuous Improvement Culture | Ensure On Time and In Full S/4 Deliverables | Define S/4 governance and delivery framework
Establish | Process | Move from Projects to Continuous Improvement Culture | Ensure On Time and In Full S/4 Deliverables | Develop OTIF tracking and value capture model
Establish | Process | Move from Projects to Continuous Improvement Culture | Ensure On Time and In Full S/4 Deliverables | Initiate cutover planning and readiness activities
Establish | Process | Move from Projects to Continuous Improvement Culture | Ensure On Time and In Full S/4 Deliverables | Enable risk tracking and escalation management
Establish | Process | Move from Projects to Continuous Improvement Culture | Ensure On Time and In Full S/4 Deliverables | Establish delivery review and governance cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Portfolio Expansion – In-house Consulting | Problem Solving | Assess current problem-solving maturity
Establish | Process | Portfolio Expansion – In-house Consulting | Problem Solving | Define problem-solving methodology and framework
Establish | Process | Portfolio Expansion – In-house Consulting | Problem Solving | Develop toolkits and standard templates
Establish | Process | Portfolio Expansion – In-house Consulting | Problem Solving | Initiate problem-solving capability programs
Establish | Process | Portfolio Expansion – In-house Consulting | Problem Solving | Launch pilot problem-solving initiatives
Establish | Process | Portfolio Expansion – In-house Consulting | Problem Solving | Establish problem-solving governance cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Portfolio Expansion – In-house Consulting | Project Management | Assess current project management maturity
Establish | Process | Portfolio Expansion – In-house Consulting | Project Management | Define PMO governance and delivery framework
Establish | Process | Portfolio Expansion – In-house Consulting | Project Management | Develop project management standards and templates
Establish | Process | Portfolio Expansion – In-house Consulting | Project Management | Initiate PM capability-building programs
Establish | Process | Portfolio Expansion – In-house Consulting | Project Management | Launch project tracking and reporting mechanisms
Establish | Process | Portfolio Expansion – In-house Consulting | Project Management | Establish project review and governance cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Portfolio Expansion – In-house Consulting | Change Management Automation | Assess current change management processes
Establish | Process | Portfolio Expansion – In-house Consulting | Change Management Automation | Define change automation framework
Establish | Process | Portfolio Expansion – In-house Consulting | Change Management Automation | Develop workflow and approval automation models
Establish | Process | Portfolio Expansion – In-house Consulting | Change Management Automation | Initiate automated change management workflows
Establish | Process | Portfolio Expansion – In-house Consulting | Change Management Automation | Enable change tracking and reporting dashboards
Establish | Process | Portfolio Expansion – In-house Consulting | Change Management Automation | Establish change governance and review cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Process | Portfolio Expansion – In-house Consulting | Analytics | Assess current analytics maturity and gaps
Establish | Process | Portfolio Expansion – In-house Consulting | Analytics | Define analytics strategy and governance framework
Establish | Process | Portfolio Expansion – In-house Consulting | Analytics | Develop KPI, reporting, and dashboard standards
Establish | Process | Portfolio Expansion – In-house Consulting | Analytics | Initiate analytics and insights enablement programs
Establish | Process | Portfolio Expansion – In-house Consulting | Analytics | Hire or onboard analytics capabilities if required
Establish | Process | Portfolio Expansion – In-house Consulting | Analytics | Establish analytics review and governance cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Technology | S/4 HANA | 100% S/4 Adoption | Assess current S/4 adoption maturity and gaps
Establish | Technology | S/4 HANA | 100% S/4 Adoption | Define S/4 adoption and governance framework
Establish | Technology | S/4 HANA | 100% S/4 Adoption | Develop user enablement and adoption roadmap
Establish | Technology | S/4 HANA | 100% S/4 Adoption | Initiate user training and change adoption programs
Establish | Technology | S/4 HANA | 100% S/4 Adoption | Enable adoption tracking and performance dashboards
Establish | Technology | S/4 HANA | 100% S/4 Adoption | Establish adoption review and governance cadence
Phase | Category | Topic | Initiative | Tasks
Establish | Technology | S/4 HANA | Tech Integrated Problem Solving and Solutioning | Assess current technology and problem-solving gaps
Establish | Technology | S/4 HANA | Tech Integrated Problem Solving and Solutioning | Define tech-enabled solutioning framework
Establish | Technology | S/4 HANA | Tech Integrated Problem Solving and Solutioning | Develop integrated tools and solution standards
Establish | Technology | S/4 HANA | Tech Integrated Problem Solving and Solutioning | Initiate technology-led problem-solving initiatives
Establish | Technology | S/4 HANA | Tech Integrated Problem Solving and Solutioning | Hire or onboard specialised technology capabilities
Establish | Technology | S/4 HANA | Tech Integrated Problem Solving and Solutioning | Establish solution review and governance cadence

## Enhance (hidden)
Phase | Category | Topic | Initiative | Tasks | Phase | Category | Topic | Initiative | Updated Task Statements
Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Assess current internal branding and engagement levels | Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Evaluate internal brand perception and engagement maturity
Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Define campaign strategy, messaging, and success metrics | Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Design campaign messaging and success measurement framework
Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Develop campaign themes, assets, and communication calendar | Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Build campaign assets and communication roadmap
Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Initiate internal engagement and branding activities | Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Activate enterprise-wide branding and engagement initiatives
Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Enable campaign participation and reach tracking | Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Monitor campaign participation and engagement effectiveness
Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Establish campaign feedback and review cadence | Enhance | People | Brand Campaign | Launch Internal Brand Campaign that Showcases Momentum | Sustain campaign feedback and improvement rhythm
Phase | Category | Topic | Initiative | Tasks | Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Review collaboration practices and engagement behaviors
Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Assess current collaboration and engagement practices | Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Design impact rituals and participation governance
Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Define impact rituals and governance structure | Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Build implementation approach for team rituals
Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Develop participation models and implementation plan | Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Roll out pilot rituals and adoption initiatives
Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Initiate pilot rituals and team adoption activities | Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Track participation and collaboration effectiveness
Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Enable participation and effectiveness tracking | Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Institutionalize ritual improvement and governance cadence
Enhance | People | New Ways of Working | Impact Rituals Designed and Implemented | Establish ritual review and improvement cadence | Enhance | People | New Ways of Working | Capability-building Programs | Analyze organizational capability and skill maturity
Phase | Category | Topic | Initiative | Tasks | Enhance | People | New Ways of Working | Capability-building Programs | Architect enterprise learning and capability framework
Enhance | People | New Ways of Working | Capability-building Programs | Assess current capability and skill maturity | Enhance | People | New Ways of Working | Capability-building Programs | Build learning curriculum and delivery pathways
Enhance | People | New Ways of Working | Capability-building Programs | Define learning and capability development framework | Enhance | People | New Ways of Working | Capability-building Programs | Deploy capability-building and training initiatives
Enhance | People | New Ways of Working | Capability-building Programs | Develop learning curriculum and delivery roadmap | Enhance | People | New Ways of Working | Capability-building Programs | Measure learning adoption and effectiveness outcomes
Enhance | People | New Ways of Working | Capability-building Programs | Initiate training and capability-building programs | Enhance | People | New Ways of Working | Capability-building Programs | Sustain continuous learning and capability governance
Enhance | People | New Ways of Working | Capability-building Programs | Enable learning effectiveness and completion tracking | Enhance | People | People Development | Job Architectures & Career Paths Set Up | Evaluate current role structures and career maturity
Enhance | People | New Ways of Working | Capability-building Programs | Establish continuous learning review cadence | Enhance | People | People Development | Job Architectures & Career Paths Set Up | Design enterprise job architecture and competency model
Phase | Category | Topic | Initiative | Tasks | Enhance | People | People Development | Job Architectures & Career Paths Set Up | Build career progression and workforce growth pathways
Enhance | People | People Development | Job Architectures & Career Paths Set Up | Assess current role and career structure maturity | Enhance | People | People Development | Job Architectures & Career Paths Set Up | Roll out career framework validation and adoption activities
Enhance | People | People Development | Job Architectures & Career Paths Set Up | Define job architecture and competency framework | Enhance | People | People Development | Job Architectures & Career Paths Set Up | Integrate career structures with HR systems and processes
Enhance | People | People Development | Job Architectures & Career Paths Set Up | Develop career progression and growth structures | Enhance | People | People Development | Job Architectures & Career Paths Set Up | Institutionalize career governance and review mechanisms
Enhance | People | People Development | Job Architectures & Career Paths Set Up | Initiate framework validation and rollout activities | Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Review employee growth and development maturity
Enhance | People | People Development | Job Architectures & Career Paths Set Up | Enable HR system and process integration | Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Design enterprise growth planning framework
Enhance | People | People Development | Job Architectures & Career Paths Set Up | Establish career framework review cadence | Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Build manager enablement and goal alignment mechanisms
Phase | Category | Topic | Initiative | Tasks | Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Launch employee growth planning and onboarding initiatives
Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Assess current employee growth and development practices | Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Monitor employee progress and development effectiveness
Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Define holistic growth planning framework | Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Sustain growth planning and review cadence
Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Develop goal-setting and manager enablement approach | Enhance | People | People Development | Learning & Development Plan | Analyze workforce learning and capability readiness
Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Initiate employee onboarding and growth planning sessions | Enhance | People | People Development | Learning & Development Plan | Design enterprise learning strategy and roadmap
Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Enable progress tracking and review mechanisms | Enhance | People | People Development | Learning & Development Plan | Build functional and behavioral learning pathways
Enhance | People | People Development | Create Holistic Growth Plan for All Employees | Establish growth plan review cadence | Enhance | People | People Development | Learning & Development Plan | Roll out learning and development interventions
Phase | Category | Topic | Initiative | Tasks | Enhance | People | People Development | Learning & Development Plan | Measure learning adoption and capability impact
Enhance | People | People Development | Learning & Development Plan | Assess current learning and capability maturity | Enhance | People | People Development | Learning & Development Plan | Institutionalize continuous learning governance
Enhance | People | People Development | Learning & Development Plan | Define learning strategy and annual roadmap | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Review CI maturity and operational improvement gaps
Enhance | People | People Development | Learning & Development Plan | Develop functional and behavioural learning tracks | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Architect CI governance and operating structure
Enhance | People | People Development | Learning & Development Plan | Initiate learning and development programs | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Build CI implementation roadmap and execution model
Enhance | People | People Development | Learning & Development Plan | Enable learning effectiveness and adoption tracking | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Launch improvement programs and CI capability initiatives
Enhance | People | People Development | Learning & Development Plan | Establish continuous learning review cadence | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Monitor CI performance and value realization metrics
[5 empty] | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Sustain CI governance and optimization cadence
Phase | Category | Topic | Initiative | Tasks | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Evaluate innovation maturity and opportunity landscape
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Assess current CI maturity and process gaps | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Design innovation governance and operating framework
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Define CI governance and operating framework | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Build innovation pipeline and idea management mechanisms
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Develop CI roadmap and implementation model | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Launch pilot innovation and collaboration initiatives
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Initiate improvement initiatives and CI training programs | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Measure innovation adoption and business impact
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Enable CI KPI tracking and reporting mechanisms | Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Institutionalize innovation review and engagement rhythm
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up a Well-functioning CI Engine | Establish CI review and sustainability cadence | Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Analyze business function readiness for transition
Phase | Category | Topic | Initiative | Tasks | Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Design pilot governance and transition success framework
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Assess current innovation maturity and opportunities | Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Build phased transition and operating model approach
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Define innovation governance and operating model | Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Execute pilot transition and operational rollout activities
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Develop innovation focus areas and idea management framework | Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Monitor pilot outcomes and operational dependencies
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Initiate pilot innovation and collaboration programs | Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Sustain pilot optimization and governance cadence
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Enable innovation KPI tracking and reporting | Enhance | Process | CoE Transition | HR CoE | Review HR process readiness and transition feasibility
Enhance | Process | Continuous Improvement Becomes a Way of Life | Set Up an Innovation Hub | Establish innovation review and engagement cadence | Enhance | Process | CoE Transition | HR CoE | Design centralized HR operating and governance model
Phase | Category | Topic | Initiative | Tasks | Enhance | Process | CoE Transition | HR CoE | Build HR service delivery and SLA mechanisms
Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Assess candidate functions and transition readiness | Enhance | Process | CoE Transition | HR CoE | Execute transition of prioritized HR operations
Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Define pilot scope, success criteria, and governance | Enhance | Process | CoE Transition | HR CoE | Monitor HR service performance and operational effectiveness
Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Develop transition and operating model framework | Enhance | Process | CoE Transition | HR CoE | Institutionalize HR governance and optimization rhythm
Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Initiate pilot transition and operational activities | Enhance | Process | CoE Transition | Procurement CoE | Analyze procurement maturity and transition scalability
Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Enable pilot performance and dependency tracking | Enhance | Process | CoE Transition | Procurement CoE | Architect centralized procurement operating framework
Enhance | Process | Core Business Function Pilot | Identify & Pilot Core Business Functions | Establish pilot review and optimisation cadence | Enhance | Process | CoE Transition | Procurement CoE | Build sourcing governance and workflow mechanisms
Phase | Category | Topic | Initiative | Tasks | Enhance | Process | CoE Transition | Procurement CoE | Roll out pilot procurement transition initiatives
Enhance | Process | CoE Transition | HR CoE | Assess HR process readiness and transition scope | Enhance | Process | CoE Transition | Procurement CoE | Track procurement compliance and value realization
Enhance | Process | CoE Transition | HR CoE | Define centralized HR operating and governance model | Enhance | Process | CoE Transition | Procurement CoE | Sustain procurement governance and review cadence
Enhance | Process | CoE Transition | HR CoE | Develop HR service delivery and SLA framework | Enhance | Process | CoE Transition | MDM CoE | Assess master data readiness and governance gaps
Enhance | Process | CoE Transition | HR CoE | Initiate transition of prioritized HR processes | Enhance | Process | CoE Transition | MDM CoE | Design enterprise data ownership and governance framework
Enhance | Process | CoE Transition | HR CoE | Enable HR performance tracking and reporting | Enhance | Process | CoE Transition | MDM CoE | Build master data standards and control structures
Enhance | Process | CoE Transition | HR CoE | Establish HR operations review and optimization cadence | Enhance | Process | CoE Transition | MDM CoE | Launch prioritized data transition and management activities
Phase | Category | Topic | Initiative | Tasks | Enhance | Process | CoE Transition | MDM CoE | Monitor enterprise data quality and reporting effectiveness
Enhance | Process | CoE Transition | Procurement CoE | Assess procurement transition readiness and scalability | Enhance | Process | CoE Transition | MDM CoE | Institutionalize data governance and review cadence
Enhance | Process | CoE Transition | Procurement CoE | Define centralized procurement operating model | Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Evaluate enterprise automation and analytics maturity
Enhance | Process | CoE Transition | Procurement CoE | Develop sourcing workflows and governance framework | Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Design integrated automation and analytics framework
Enhance | Process | CoE Transition | Procurement CoE | Initiate pilot procurement transition activities | Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Build prioritized automation and AI implementation roadmap
Enhance | Process | CoE Transition | Procurement CoE | Enable procurement compliance and reporting controls | Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Deploy automation, AI, and analytics transformation initiatives
Enhance | Process | CoE Transition | Procurement CoE | Establish procurement review and value realization cadence | Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Measure automation adoption and business value realization
Phase | Category | Topic | Initiative | Tasks | Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Sustain automation governance and optimization rhythm
Enhance | Process | CoE Transition | MDM CoE | Assess master data transition readiness and gaps
Enhance | Process | CoE Transition | MDM CoE | Define enterprise data governance and ownership model
Enhance | Process | CoE Transition | MDM CoE | Develop master data standards and control framework
Enhance | Process | CoE Transition | MDM CoE | Initiate prioritized data management transition activities
Enhance | Process | CoE Transition | MDM CoE | Enable centralized data reporting and monitoring
Enhance | Process | CoE Transition | MDM CoE | Establish data governance review cadence
Phase | Category | Topic | Initiative | Tasks
Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Assess current automation and analytics landscape
Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Define enterprise automation and analytics framework
Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Develop prioritized use-case and implementation roadmap
Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Initiate automation, AI, and analytics deployment programs
Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Enable centralized monitoring and value tracking
Enhance | Technology | Automation Strategy | Harmonize Mining, RPA, AI, Data Analytics | Establish automation governance and review cadence

## Optimize (hidden)
Phase | Category | Topic | Initiative | Tasks | Phase | Category | Topic | Initiative | Updated Task Statements
Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Assess performance culture maturity and ownership gaps | Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Evaluate performance culture maturity and ownership behaviors
Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Define enterprise performance culture framework | Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Design enterprise-wide high-performance culture framework
Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Develop KPI alignment and ownership mechanisms | Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Build KPI alignment and accountability mechanisms
Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Initiate recognition, feedback, and performance interventions | Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Roll out recognition and performance enhancement initiatives
Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Enable culture and performance maturity tracking | Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Monitor culture adoption and performance effectiveness
Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Establish continuous performance review cadence | Optimize | People | Performance Culture | Measures Designed to Shift & Sustain High Performance and Ownership Culture | Institutionalize performance governance and review rhythm
Phase | Category | Topic | Initiative | Tasks | Optimize | People | Learning Organization | New Ways of Working Sustained | Analyze adoption maturity of new ways of working
Optimize | People | Learning Organization | New Ways of Working Sustained | Assess adoption maturity of new ways of working | Optimize | People | Learning Organization | New Ways of Working Sustained | Architect continuous learning and collaboration framework
Optimize | People | Learning Organization | New Ways of Working Sustained | Define continuous learning and collaboration framework | Optimize | People | Learning Organization | New Ways of Working Sustained | Build cross-functional innovation and learning mechanisms
Optimize | People | Learning Organization | New Ways of Working Sustained | Develop cross-functional learning and innovation mechanisms | Optimize | People | Learning Organization | New Ways of Working Sustained | Activate continuous learning and collaboration initiatives
Optimize | People | Learning Organization | New Ways of Working Sustained | Initiate continuous learning and collaboration programs | Optimize | People | Learning Organization | New Ways of Working Sustained | Measure adoption effectiveness and workforce engagement
Optimize | People | Learning Organization | New Ways of Working Sustained | Enable adoption and effectiveness tracking | Optimize | People | Learning Organization | New Ways of Working Sustained | Sustain continuous learning and improvement cadence
Optimize | People | Learning Organization | New Ways of Working Sustained | Establish continuous improvement and learning cadence | Optimize | People | Employee Experience | Redesign Employee Life Cycle | Evaluate employee lifecycle experience and engagement gaps
Phase | Category | Topic | Initiative | Tasks | Optimize | People | Employee Experience | Redesign Employee Life Cycle | Design future-ready employee experience framework
Optimize | People | Employee Experience | Redesign Employee Life Cycle | Assess employee lifecycle experience and engagement gaps | Optimize | People | Employee Experience | Redesign Employee Life Cycle | Build standardized employee journey and interaction models
Optimize | People | Employee Experience | Redesign Employee Life Cycle | Define future-state employee experience framework | Optimize | People | Employee Experience | Redesign Employee Life Cycle | Deploy digital employee experience enhancement initiatives
Optimize | People | Employee Experience | Redesign Employee Life Cycle | Develop standardized employee journey and touchpoint model | Optimize | People | Employee Experience | Redesign Employee Life Cycle | Monitor employee satisfaction and engagement insights
Optimize | People | Employee Experience | Redesign Employee Life Cycle | Initiate digital employee experience enhancement programs | Optimize | People | Employee Experience | Redesign Employee Life Cycle | Institutionalize employee experience optimization cadence
Optimize | People | Employee Experience | Redesign Employee Life Cycle | Enable employee feedback and satisfaction tracking | Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Analyze strategic function transition readiness and dependencies
Optimize | People | Employee Experience | Redesign Employee Life Cycle | Establish employee experience review and optimization cadence | Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Design transition governance and operating framework
Phase | Category | Topic | Initiative | Tasks | Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Build phased transition and service delivery roadmap
Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Assess strategic business functions and transition readiness | Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Execute prioritized business function transition activities
Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Define transition governance and operating framework | Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Track transition continuity and operational effectiveness
Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Develop phased transition and service delivery roadmap | Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Sustain transition governance and optimization rhythm
Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Initiate prioritized business function transition activities | Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Review process documentation maturity and KPI visibility
Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Enable transition performance and continuity tracking | Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Design process governance and measurement architecture
Optimize | Process | Core Business Transitions | Identification of Core Business Support to be Transitioned | Establish transition optimization and governance cadence | Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Build operational dashboards and process visibility mechanisms
Phase | Category | Topic | Initiative | Tasks | Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Launch workflow optimization and continuous improvement initiatives
Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Assess current process documentation and KPI maturity | Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Monitor real-time process performance and reporting effectiveness
Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Define process governance and measurement framework | Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Institutionalize process excellence and improvement cadence
Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Develop operational dashboards and visibility mechanisms | Optimize | Process | Process Excellence | Global Standards Maintained | Evaluate operational maturity against global benchmarks
Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Initiate continuous improvement and workflow optimization activities | Optimize | Process | Process Excellence | Global Standards Maintained | Architect enterprise governance and quality standards framework
Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Enable real-time process tracking and reporting | Optimize | Process | Process Excellence | Global Standards Maintained | Build standardized compliance and control mechanisms
Optimize | Process | Process Excellence | Processes Documented and Measured Constantly | Establish process review and improvement cadence | Optimize | Process | Process Excellence | Global Standards Maintained | Roll out global process harmonization initiatives
Phase | Category | Topic | Initiative | Tasks | Optimize | Process | Process Excellence | Global Standards Maintained | Monitor enterprise operational risks and compliance effectiveness
Optimize | Process | Process Excellence | Global Standards Maintained | Assess operational maturity against global standards | Optimize | Process | Process Excellence | Global Standards Maintained | Sustain standards governance and operational maturity reviews
Optimize | Process | Process Excellence | Global Standards Maintained | Define enterprise-wide governance and quality framework | Optimize | Process | Process Excellence | Push for Max Digital | Assess enterprise digital maturity and automation opportunities
Optimize | Process | Process Excellence | Global Standards Maintained | Develop standardized controls and compliance mechanisms | Optimize | Process | Process Excellence | Push for Max Digital | Design digital transformation and governance framework
Optimize | Process | Process Excellence | Global Standards Maintained | Initiate global process alignment and standardization activities | Optimize | Process | Process Excellence | Push for Max Digital | Build prioritized automation and digital enablement roadmap
Optimize | Process | Process Excellence | Global Standards Maintained | Enable centralized monitoring of operational risks and standards | Optimize | Process | Process Excellence | Push for Max Digital | Deploy intelligent workflows and digital platforms
Optimize | Process | Process Excellence | Global Standards Maintained | Establish operational maturity and standards review cadence | Optimize | Process | Process Excellence | Push for Max Digital | Measure digital adoption and operational performance impact
Phase | Category | Topic | Initiative | Tasks | Optimize | Process | Process Excellence | Push for Max Digital | Institutionalize digital optimization and governance cadence
Optimize | Process | Process Excellence | Push for Max Digital | Assess digital transformation opportunities and maturity | Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Evaluate business, process, and technology alignment maturity
Optimize | Process | Process Excellence | Push for Max Digital | Define digital governance and transformation framework | Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Architect integrated business-process-technology framework
Optimize | Process | Process Excellence | Push for Max Digital | Develop prioritized digital and automation roadmap | Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Build cross-functional transformation and governance roadmap
Optimize | Process | Process Excellence | Push for Max Digital | Initiate digital platform and intelligent workflow adoption | Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Roll out digital enablement and workflow transformation initiatives
Optimize | Process | Process Excellence | Push for Max Digital | Enable data-driven decision-making and digital performance tracking | Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Monitor technology adoption and operational business impact
Optimize | Process | Process Excellence | Push for Max Digital | Establish digital maturity and optimization cadence | Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Sustain enterprise technology governance and optimization rhythm
Phase | Category | Topic | Initiative | Tasks | Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Analyze techno-functional capability maturity and future readiness
Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Assess business, process, and technology alignment gaps | Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Design integrated techno-functional capability framework
Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Define integrated business-process-technology framework | Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Build digital, automation, and AI learning pathways
Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Develop cross-functional governance and transformation roadmap | Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Launch hands-on learning and cross-functional capability initiatives
Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Initiate digital workflow and technology enablement programs | Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Measure workforce capability growth and business applicability
Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Enable operational impact and adoption tracking | Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Institutionalize future-ready capability review cadence
Optimize | Technology | Reposition Tech as Enabler and Align | Tech → Process → People | Establish technology optimization and governance cadence | Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Assess enterprise innovation and experimentation readiness
Phase | Category | Topic | Initiative | Tasks | Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Design innovation governance and prioritization framework
Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Assess current techno-functional capability maturity | Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Build sandbox and rapid prototyping enablement structures
Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Define techno-functional learning and capability framework | Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Activate innovation sprints and prototyping initiatives
Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Develop specialized digital, automation, and AI learning pathways | Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Track innovation outcomes and value realization effectiveness
Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Initiate hands-on learning and cross-functional collaboration programs | Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Sustain innovation governance and scaling cadence
Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Enable capability maturity and business applicability tracking | Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Evaluate AI readiness and operational use-case potential
Optimize | Technology | Tech Embedded Capability Building | Develop Techno-Functional Expertise | Establish future-ready capability review cadence | Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Architect responsible AI governance and usage framework
Phase | Category | Topic | Initiative | Tasks | Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Build AI adoption and business integration roadmap
Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Assess innovation and experimentation opportunities | Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Deploy AI-enabled workflows and capability-building initiatives
Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Define innovation governance and prioritization framework | Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Monitor AI adoption and business value realization
Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Develop sandbox, pilot, and prototyping enablement model | Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Institutionalize AI governance and optimization cadence
Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Initiate innovation sprints and rapid prototyping programs
Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Enable innovation outcome and value realization tracking
Optimize | Technology | Tech Embedded Capability Building | Encourage Rapid Prototyping and Innovation | Establish innovation review and scaling cadence
Phase | Category | Topic | Initiative | Tasks
Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Assess AI readiness and operational use-case opportunities
Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Define AI governance and responsible usage framework
Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Develop AI adoption and business integration roadmap
Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Initiate AI-enabled workflows and capability-building programs
Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Enable AI adoption and business outcome tracking
Optimize | Technology | Tech Embedded Capability Building | Problem Solving in the Era of AI | Establish AI optimization and governance cadence